## Sheet1
PRELIMINARY EVALUATION REPORT (PER) CHECKLIST
FORMER SATRALLOY SITE (JEFFERSON COUNTY, OH)
RI/FS SOW Task Description | Completed | In RI/FS Work Plan | Not Relevant | Notes
Appendix A of SOW
I. Description of Current Conditions | X | Sections 1 and 3
A. Existing Analytical Data | X | Section 3
B. Site Visit | X | Section 3
C. Site Background | X | Section 1.1
1. Maps
a. General geographic location | X | Figure 1-1
b. Property lines and owners | X | Figure 1-2, Section 1.1.2
c. Topography and surface drainage | X | Figures 1-2 and 3-5
d. Tanks, buildings, utilities, paved areas etc. | X | Figure 1-2
e. Waste TSD areas and dates of operation |  |  | X | No permitted waste disposal
f. Product and waste USTs and piping |  | Section 6.4 |  | USTs formerly present; may have been removed
g. Locations of spills or releases of contaminants | X | Figures 1-3 thru 1-7
h. Surrounding land uses and zoning designations | X | Section 1.1.1
i. Wetlands and surface water bodies | X | Figures 1-2 and 3-3
j. Previous sampling locations and dates for all media | X | Figure 3-1
k. Location of all wells (monitoring and supply) | X | Figures 1-2, 1-3, and 6-1; Section 4.1.3.2 (oil and gas wells) Figure 3-1 (existing wells) & Figure 6-1 (RI MWs)
l. Federal sole source aquifer designations and drinking water source water protection areas |  |  | X | Not a designated sole source aquifer
2. History and description of ownership and operation | X | Section 1.1.2
3. Dates of past product or waste spills or discharges and materials, amount, and location and any response actions | X | Section 1.1.3
4. Summary of permits and list of related documents | X | Section 1.1.3
5. Summary of enforcement actions and list of related documents | X | Section 1.1.3
6. Violations of permits and related documents | X | Section 1.1.3
7. Summary of previous response actions | X | Section 1.1.3
8. Summary of known or suspected source areas | X | Sections 3.2, 3.3, and 3.4
D. Nature and Extent of Contamination |  | Section 3 and Appendix C
E. Conceptual Site Model | X | Section 4 and Fig. 4-1 |  | Preliminary
II. Review and Integration of Emergency or Interim Actions | X | Section 2.3.2
III. Evaluation of Remedial Action Technologies, Process Options, and Broadly Defined Remedial Alternatives |  | Section 2.3.6
A. Technologies and process options |  | Section 2.3.6.3
B. Preliminary list of remedial alternatives |  | Section 2.3.6.4
C. Evaluate need for treatability studies |  | Section 2.3.6.5
D. Preliminary ARARs and TBC criteria |  | Section 2.3.6.2
IV. Data Needs and Data Usage |  | Section 5
A. Define Source Areas of Contamination |  | Section 5
B. Define Nature and Vertical and Horizontal Extent of Contamination |  | Section 5
C. Define Environmental Setting |  | Sections 3 and 4.1
D. Define Potential Pathways of Contaminant Migration |  | Sections 5.3, 5.4, and 5.5
E. Define Hot Spots |  | Section 3.1; Appendix C
F. Define Potential Receptors | X | Table 2-4; Sections 4.2 and 4.3
G. Support the HHRA and ERA |  | Section 5, Appendix D
H. Support Development and Evaluation of Remedial Alternatives |  | Section 5
Appendix E of SOW - Environmental Setting
I. Regional Hydrogeology |  | Section 4.1
A. Depth to Bedrock |  | Section 4.1.1
B. Hydrostratigraphic unit correlation |  | Section 4.1.2; Figure 3-2
C. Aquifer and aquitard delineation |  | Section 4.1.3
D, Active and inactive wells (within 4 mile radius of site) |  | Figure 6-1
E. Well logs, well construction details, and average yield |  | Section 5.5
F. Average pumping rates of production wells |  |  | X | No operating production wells
G. Ambient groundwater quality characterization |  | Sections 3.1.2 and 6.8
H. Average depth to water |  | Sections 3.1.2 and 6.8
I. Seasonal variation in groundwater flow direction |  | Section 6.8
J. Recharge and discharge area identification |  | Section 6.8
K. Source water protection area identification |  | Section 6.8
L. Aquifer designation (i.e. Sole Source Aquifer) |  | Section 6.8
M. Regional geomorphology and topography |  | Sections 3.4 and 4.1; Figure 1-2
N. Structural feature delineation (bedding planes and fold, joint, and fracture trace orientation |  | Sections 3.4 and 4.1
II. Site Hydrogeology |  | Section 4.1 and 6.8
A. Classification and description of stratigraphic units |  | Section 4.1 and 6.8
1. Hydraulic conductivity (vertical and horizontal) |  | Section 4.1 and 6.8
2. Porosity, effective porosity, and bulk density |  | Section 4.1 and 6.8
3. Rock and soil (ASTM 2488 and 2487) classification |  | Section 4.1 and 6.8
4. Grain size distribution (sieve and hydrometer) curves |  | Section 4.1 and 6.8
5. Moisture content |  | Section 4.1 and 6.8
6. Attenuation capacity and mechanisms (ion exchange, base saturation, organic carbon content, mineral content, soil sorptive capacity, storage capacity) |  | Section 4.1 and 6.8
7. pH |  | Section 4.1 and 6.8
B. Surface Soils |  | Sections 5.3 and 6.9
1. SCS soil classification |  | Sections 5.3 and 6.9
2. Surface soil distribution |  | Sections 5.3 and 6.9
3. Depth and profile |  | Sections 5.3 and 6.9
4. Organic carbon content |  | Sections 5.3 and 6.9
5. pH |  | Sections 5.3 and 6.9
6. Porosity (total, air-filled) |  | Sections 5.3 and 6.9
7. Bulk density |  | Sections 5.3 and 6.9
8. Gravimetric soil moisture content |  | Sections 5.3 and 6.9
9. Fraction of vegetative cover (of contaminated areas) |  | Sections 5.3 and 6.9
10. Ion exchange capacity |  | Sections 5.3 and 6.9
11. Infiltration |  | Sections 5.3 and 6.9
12. Evapotranspiration |  | Sections 5.3 and 6.9
C. Local Groundwater Flow Regime |  | Section 4.1 and 6.8
1. Identification of aquitards and aquifer systems |  | Section 4.1 and 6.8
2. Identification of saturated zones |  | Section 4.1 and 6.8
3. Identification of water table and potentiometric surface depth with seasonal fluctuation |  | Section 4.1 and 6.8
4. Seasonal groundwater flow direction for each aquifer system and/or poteniometric maps for each significant zone of saturation |  | Section 4.1 and 6.8
5. Flow rate throughout each aquifer system |  | Section 4.1 and 6.8
6. Horizontal and vertical gradients |  | Section 4.1 and 6.8
7. Infiltration rates through the unsaturated zone |  | Section 4.1 and 6.8
8. Flow across and lateral to hydrostratigraphic units including seepage and upward leakage |  | Section 4.1 and 6.8
9. Flow budget across the Site with recharge and discharge areas |  | Section 4.1 and 6.8
10. Location of nearest hydraulic boundaries |  | Section 4.1 and 6.8
11. Ambient groundwater chemistry upgradient and |  | Section 4.1 and 6.8
downgradient of the Site |  | Section 4.1 and 6.8
12. Hydrotratigraphic cross sections with horizontal and lateral extent, depth, and thickness of units, both longitudinal and transverse to dominant flow direction. Include flow nets with vertical and horizontal flow components. |  | Section 4.1 and 6.8
13. Delineate structural features, including orientation, density and distribution |  | Section 4.1 and 6.8
D. Description of man-made influences affecting hydrogeology | X | Section 4.1.3
1. Active and inactive supply and production wells and schedules | X | Section 4.1.3.2 (Oil and Gas Wells); Figures 1-2, 1-3, and 6-1
2. Man-made structures such as injection wells, pipelines, french drains, ditches, unlined and lined ponds, lagoons, septic tanks, NPDES permitted outfalls, retention areas, utility lines. |  | Section 4.1.3; Figures 1-2, 1-3, and 6-1
E. Geomorphology of the Site | X | Section 4.1
1. Topographic features that may influence groundwater flow | X | Section 4.1.3; Figure 1-2
2. Surface topographic map depicting streams, wetlands, topographic depressions and springs with adequate contour intervals (e.g. two-foot) and all borings, monitoring wells and cross-sections. |  | Figures 3-3 and 6-1
F. RI Report Field Methods |  | Section 6; Appendix F
1. Borehole characterization |  | Section 6.9.2
2. Groundwater level measurement |  | Section 6.8.1
3. Groundwater sampling |  | Section 6.8.1
4. Monitoring well and piezometer installation |  | Section 6.8.1
5. Aquifer testing |  | Section 6.8.1
6. Remote sensing |  |  | X
7. Groundwater tracer testing |  |  | X
8. Isotopic age dating |  |  | X
III. Surface Water and Sediment
A. Description of perennial and ephemeral surface water bodies | X | Sections 1.1.1 and 3.7
1. Lakes, estuaries and impoundments - Location, elevation, surface area, inflow, outflow, depth, temperature stratification, and volume |  |  | X | None near site
2. Streams, ditches, drains, wetlands and channels - location, hydraulic gradient, flow velocity, base flow, depth, width, bank height and slope, gaining and losing stream sections, seasonal fluctuations, stabilization of stream bed, description of stream banks, flood plain areas, and flood zones |  | Figure 3-4; Sections 3.8, 5.4, 5.7, and 6.7
3. Drainage patterns/storm water runoff | X | Figure 3-5; Section 3.10
4. Groundwater seepage and/or recharge to surface water |  | Sections 4.1.3, 5.4, and 6.6
5. Known discharges including NPDES permitted |  | Figure 3-5
B. Chemical, physical, and biological/biochemical characteristics of surface water and sediments |  | Sections 6.10, 6.6, & 6.7; Appendix C
1. Chemical (surface water and sediments) |  | Sections 3, 5, and 6
a. Total organic carbon (TOC) |  |  | X | Inorganic COPCs
b. pH |  | Table 6-1
c. total dissolved solids (TDS) |  | Table 6-1
d. total suspended solids (TSS) |  | Table 6-1
e. biological oxygen demand (BOD) |  |  | X | Inorganic COPCs
f. conductivity |  | Table 6-1
g. dissolved oxygen |  | Table 6-1
h. hazardous chemicals of potential concern |  | Sections 3, 5, and 6
2. Physical (surface water and sediments) |  | Table 6-1
a. temperature |  | Table 6-1
b. particle/grain size |  | Table 6-1
c. appearance/texture/odor/color |  | Sections 5.6 and 5.8; Table 6-1
d. organic matter deposition |  | Sections 5.6 and 5.8
e. deposition area, patterns, rates |  | Sections 5.6 and 5.8
f. thickness profile |  | Sections 5.6 and 5.8
3. Biological/biochemical
a. aquatic life use designation (based on Ohio Water Quality Standards) |  | Section 3.7, Appendix D
b. attainment status of water body |  | Appendix D
c. Ohio wetland classification |  | Section 3.8
4. Field Methods and Procedures (streams) |  | Appendix E
a. drain tracer studies |  |  | X
b. seepage meter installations and data acquisition |  |  | X
c. stream piezometer installation and water level measurements |  |  | X
d. stream weir gauge installation and data acquisition |  |  | X
IV. Local Climate |  | To be presented in the RI Report
A. Annual and monthly rainfall averages |  | To be presented in the RI Report
B. Monthly temperature averages and extremes |  | To be presented in the RI Report
C. Wind speed and direction |  | To be presented in the RI Report
D. Relative humidity/dew point |  | To be presented in the RI Report
E. Atmospheric pressure |  | To be presented in the RI Report
F. Evaporation data |  | If relevant
G. Development of inversions |  | If relevant
H. Climate extremes and frequency of occurrence |  | As relevant
I. Topographic features that may affect airflow or emissions patterns |  | Section 4.1.3; Figure 1-2
V. Human receptors potentially exposed to Site-related contaminants |  | Sections 2.3.4.4 and 4.2
A. Human population data including demographics |  | Table 2-4
B. Sensitive sub-populations |  | Section 2.3.4.4.4 and 4.2.1
C. Populations served by surface water intakes or groundwater wells |  | Section 3.5; Appendix C | X | No detectable contamination of Cross Creek by Site COPCs
D. Land use (e.g. residential, commercial, recreational) |  | Table 2-4
VI. Ecological receptors potentially exposed to Site-related contaminants |  | Sections 2.3.4.5, 3.7, and 4.3; Appendix D
A. Terrestrial receptors |  | Section 4.3
B. Aquatic receptors |  | Section 4.3
C. Special interest species (e.g. threatened or endangered species) |  | Section 3.11
Appendix F Source Characterization |  | Sections 3.1.1, 3.2, 3.3, 3.4, and 6.5
I. Unit/Disposal Area |  | Sections 3.1.1, 3.2, 3.3, 3.4, and 6.5
II. Waste/Contaminant Characteristics |  | Sections 3.1.1, 3.2, 3.3, 3.4, and 6.5
A. Type of waste |  | Sections 3.1.1, 3.2, 3.3, 3.4, and 6.5
1. Waste types and classification (e.g. RCRA, TSCA etc.) |  | Sections 3.1.1, 3.2, 3.3, 3.4, and 6.5
2. Quantity |  | Sections 3.1.1, 3.2, 3.3, 3.4, and 6.5
3. General chemical class (e.g. acid, base, solvent, metals etc.) |  | Sections 3.1.1, 3.2, 3.3, 3.4, and 6.5
B. Waste/contaminant physical and chemical properties |  | Sections 3.1.1, 3.2, 3.3, 3.4, and 6.5
1. Phase (e.g. solid, liquid, gas) |  | Sections 3.1.1, 3.2, 3.3, 3.4, and 6.5
2. Physical description (e.g. powder, oily sludge) |  | Sections 3.1.1, 3.2, 3.3, 3.4, and 6.5
3. Temperature |  | Sections 3.1.1, 3.2, 3.3, 3.4, and 6.5
4. pH |  | Sections 3.1.1, 3.2, 3.3, 3.4, and 6.5
5. Molecular weight |  |  | X
6. Density |  |  | X
7. Boiling point |  |  | X
8. Viscosity |  |  | X
9. Water solubility |  |  | X
10. Cohesiveness of wastes |  |  | X
11. Vapor pressure |  |  | X
12. Henry's law constant |  |  | X
13. Kow |  |  | X
14. Kd |  |  | X
15. Flash point |  |  | X
C. Waste/contaminant migration and dispersal characteristics
1. Retardation |  |  | X
2. Biodegradation rates |  |  | X
3. Photodegradation rates |  |  | X
4. Hydrolysis rates |  |  | X
5. Chemical transformation rates and degradation products |  | Sections 3.1.1, 3.2, 3.3, 3.4, and 6.5
6. Chemical interactions |  | Sections 3.1.1, 3.2, 3.3, 3.4, and 6.5
7. Products of all such reactions or processes |  | Sections 3.1.1, 3.2, 3.3, 3.4, and 6.5
8. Leachate infiltration rates and mass loading to aquifer systems |  | Sections 3.1.1, 3.2, 3.3, 3.4, and 6.5
9. Soil screening concentrations |  | Sections 3.1.1, 3.2, 3.3, 3.4, and 6.5
Appendix G - Nature and Extent of Contamination
I. Groundwater contamination |  | Sections 3.1.2 and 5.5
A. Horizontal and vertical extent of immiscible or dissolved phase plumes and discharges to surface water for compliance with Water Quality Standards |  | Sections 3.1.2 and 5.5
B. Delineation of contaminant specific flow velocity vectors in map and profile |  | Sections 3.1.2 and 5.5
C. Contaminant specific isopleths in map and profile for each aquifer system |  | Sections 3.1.2 and 5.5
D. Extrapolation of future contaminant migration rates and distribution |  | Sections 3.1.2 and 5.5
E. Identification & sampling of production wells in vicinity of contamination |  | Sections 3.1.2 and 5.5
F. Seasonal variation of groundwater contaminant concentrations |  | Sections 3.1.2 and 5.5
II. Surface and subsurface soil contamination |  | Sections 3.8 and 6.9
A. Vertical and horizontal extent and pattern of contamination |  | Sections 3.8 and 6.9
B. Contaminant and soil chemical, biological, and physical properties |  | Sections 3.8 and 6.9
C. Delineation of contaminant specific concentrations |  | Sections 3.8 and 6.9
D. Mechanisms and patterns of soil contaminant migration |  | Section 4
E. Extrapolation of future soil contaminant movement |  | Section 4
III. Surface Water and Sediment Contamination |  | Sections 3.1.4, 3.5, 6.6, 6.7, and 6.10
A. Horizontal and vertical extent of immiscible or dissolved phase plumes in surface water, sediments, and seeps |  |  | X
B. Horizontal and vertical distribution of any immiscible, dissolved or suspended surface water contamination |  |  | X
C. Horizontal and vertical distribution of sediment and pore water contamination |  | Sections 5.8 and 6.10
D. Velocity and direction of contaminant migration in surface water and sediment |  | Sections 3.1.4, 3.5, 6.6, 6.7, and 6.10
E. Evaluation of physical, biological, and chemical factors influencing chemical migration |  | Sections 3.1.4, 3.5, 6.6, 6.7, and 6.10
F. Extrapolation of future contaminant migration |  | Section 4
IV. Subsurface Gas Contamination |  |  | X
V. Air Contamination |  | See Air Monitoring Workplan
VI. Other media (based on anticipated receptors)
A. Vegetation |  | Section 2.3.4.5
B. Macroinvertebrates |  | Sections 3.1.5 and 3.1.6
C. Fish | X | Sections 3.1.6 and 5.10
D. Shellfish |  |  | X
E. Prey |  | Section 2.3.4.5
Appendix H - Human Health Risk Assessment | X | Section 2.3.4.4
Appendix I - Ecological Risk Assessment | X | Section 2.3.4.5